## Sheet1
BugType	BugSeverity	PhaseIntroduce	PhaseDetected	BugStatus	Resolution	Pagetitle	Details	Attachment	Comment	Status
Bug(UI)	Minor	Construction	Module / Integration Testing	Open	Unresolved	General	a) On page load the focus should be set on first control of the page. / b) The button sizes should be same in a such a way that text on that / button properly gets fit-in and also some space is left, it should not / Be conjusted. / c) Tabbing should be provided to traverse across all fields.	generalUIBug01.png	a). Done. / b). Done. / c).It is By Default Provided By The Browser	Solved
Bug(UI)	Minor	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	In message show the same field name as given in the form. / For example, for field Craft number in validation message / "Craft Number1" is coming.	crtApptUI01.png	Done	Solved
Bug(UI)	Minor	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	a) Provide validation message for as many fields that are mandatory. For example, Remark and Type of Appointment fields are marked mandatory (asterisks mark) but in required field validation message those fields are not coming though kept empty. / b) Also if fields are not mandatory then do not provide asterisks mark to such fields.	crtApptUI02.png	Done	Solved
Ambiguity	Major	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	The Add more button is applicable only on Craft number field?		Yes	Solved
Bug(Functional)	Major	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	The message “No more textbox to remove” should come immediately on one click it no text-boxes exist to remove. On two clicks the message appears.	crtApptFunc02.png	Done	Solved
Bug(Functional)	Major	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	a) Click on Add More button. Add 2 test boxes. / b) Then click on Remove Last button more than 2 times that is 4 times exactly. / c) Message comes “No more text box to remove”, click OK. / d) Then again click on Add More button and add one text box and then click on Remove Last button, the text box added is not getting removed even on several trials.	crtApptFunc0101.png, crtApptFunc0102.png, crtApptFunc0103.png, crtApptFunc0104.png, crtApptFunc0105.png	Done	Solved
Bug(Functional)	Major	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	a) Add another text-box to Craft Number field but do not enter value in it. / b) Fill in another details and click on save. Validation message comes to enter value in another text boxt of the Craft number field, that's fine. / c) Enter value in text-box2 of Craft Number and then again click on Submit, the record does not gets Saved. / d) Moreover the time selected in Date/Time field resets and user is not able to select either as no values populated. User has to reselect date and then only it can set. / e) Also the Transaction Type field selection goes away. The selected transaction types should remain expanded with selections done.	crtApptFunc0301.png, crtApptFunc0302.png, crtApptFunc0303.png	Done	Solved
Bug(Functional)	Critical	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	Two appointments on same time and date should not be allowed to be added.	crtApptFunc0401.png, crtApptFunc0402.png, crtApptFunc0403.png	It Should be allowed	Solved
Bug(Functional)	Major	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	Email and numeric fields validations are not implemented. Also of Phone numbers.		Done	Solved
Bug(Functional)	Critical	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	On saving the appointment, in summary that is displayed, at the bottom sometimes "I agree the terms and conditions" check-box appears and sometimes not. Moreover on checking the check-box there's no button to save it.	crtApptFunc0501.png, crtApptFunc0502.png	Done	Solved
Bug(UI)	Minor	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	In validation message popped up the word "more" is misspelled.	crtApptUI04.png	Done	Solved
Bug(Functional)	Major	Construction	Module / Integration Testing	Open	Unresolved	General	- Spaces and null value should be handled. Instead of actual value user simply enters spaces then proper validations should be fired like for mandatory field if space is entered Required Validation should be fired and space should not be accepted. / - Also remove all white spaces from the beginning and ending of the string.		Done	Solved
Bug(UI)	Minor	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	In IE9 and Firefox when clicked on Add more text the new text box is added in such a way that no space is left between the two text boxes of Craft Number field.	crtApptUI05.png	Done	Solved
Bug(UI)	Minor	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	a) The alignment of text displayed is not proper. / b) Also craft number field's value is shown in square brackets and extra slash appears at the end of Passport Number field. / c) Also Appoint Details text should appear in one line.	crtApptSummUI01.png	Done / c) Not Required	Solved
Enhancement	Minor	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/login/ / LoginForm.mpa	Provide a link to move back to Appointment form from login page.	loginEnhnc01.png	Already Available..By Clicking Logo You can Redirect to home page From Whole Site	Solved
Bug(UI)	Major	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/login/ / LoginForm.mpa	When Forgot Password link is clicked the backgorund vanishes.	loginUI01.png	It's ColorBox Effect	Solved
Bug(Functional)	Major	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/login/ / LoginForm.mpa	1) If email id needs to be provided, as per the instruction, then change the field label to "Enter Email Id". / 2) Make "Close" button's text bold and bigger. / 3) Email id field should be mandatory. Provide asterisk mark and also implement mandatory validation.	loginFunc01.png	1.)User will provide userID And the mail will sent to the email Id registered with that userIId / 2,3).Done	Solved
Bug(UI)	Minor	Construction	Module / Integration Testing	Open	Unresolved	http://192.168.1.152:8080/MPA_OAS/appointment/ / AppointmentForm.mpa	In IE9 and Firefox when clicked on Add more text the new text box is added in such a way that no space is left between the two text boxes of Craft Number field.		Done	Solved